PRIVATE DEVELOPER STAKEHOLDER GUIDE Next-Generation BESS Siting Tool How to Use the Tool · What Risks It Surfaces · How to Shorten Time-to-Permit Chelsea & Everett, MA · Selected as Top Investment Sites Monzia Moodie, Regulatory & Policy Systems Analyst · Kadir Farah, Storage Systems & Development Specialist Advisor: Marcus Anum · Sponsor: Ledum Nordee · TPS × MassDOER Fellowship · April 2026

EXECUTIVE SUMMARY

This guide is written for private BESS developers considering projects in Massachusetts. It explains how the Next-Generation BESS Siting Tool works, what critical risks it surfaces before site selection, how it compresses the permitting timeline, and why Chelsea and Everett emerged as the two highest-scoring investment sites in Suffolk and Middlesex Counties. The analysis integrates Environmental Justice compliance, grid hosting capacity, zoning law, physical feasibility, and ISO-NE revenue modeling into a single five-layer Multi-Criteria Evaluation framework validated by two real Section 83E Round 1 project selections.

|  | BOTTOM LINE FOR DEVELOPERS Massachusetts projects that do EJ screening, CIA analysis, and hosting capacity review before site acquisition close deals faster, face fewer community objections, and access a deeper incentive stack — including federal ITC up to 70% in EJ brownfield locations. The tool does this work automatically, before you commit capital. |
| --- | --- |

1.  WHY BESS PROJECTS FAIL BEFORE THEY START

Massachusetts has a 5,000 MW storage mandate by July 2030 (Chapter 239, Acts of 2024) — the nation’s most ambitious. Yet only 644 MWh is installed statewide. The buildout gap is not capital or technology. It is siting. Four recurring failure modes drive late-stage cost and delay:

| Failure Mode | What Happens | Cost Consequence |
| --- | --- | --- |
| EJ screening done late | Site selected before CIA triggers are checked; redesign required after permitting starts | 6–18 month delays; $500K–$2M in redesign costs |
| Setback rules unknown | Battery MW footprint oversized for available buildable area | MW capacity must be cut; economics re-underwritten |
| Revenue not zone-specific | ISO-NE Hub average used; NEMA/SENE premium, CPS multipliers ignored | IRR understated; may not clear investment committee |
| Hosting capacity not checked | Interconnection cost estimated as a placeholder | Actual upgrade bill (e.g. $4M transformer) kills project return |

|  | KEY REGULATORY RISK — MARCH 2026 Mandatory Cumulative Impact Analysis (CIA) is now required for all BESS projects in EJ communities before state permitting (980 CMR 15.00, OEJE CIA Standards issued January 23, 2026). All 13 municipalities in the Suffolk + Middlesex study area are EJ-designated. Developers who do not build CIA into their project development timeline will face permitting holds. |
| --- | --- |

2.  HOW THE TOOL WORKS: FIVE-LAYER WALKTHROUGH

The BESS Siting Tool applies a five-layer Multi-Criteria Evaluation (MCE) framework to every candidate municipality in the study area. Each layer scores from 0 to 25 points, producing a maximum composite score of 125. Scores are generated from publicly accessible data sources updated on an ongoing basis — no proprietary data feeds required.

Layer 1: Environmental Justice & Regulatory Compliance

The tool queries the MassGIS 2020 OEJE EJ Population Layer to flag EJ block group designation status for every parcel in the study area. EJ designation is triggered by any of four statutory criteria: minority population ≥40%, median household income ≥65% of statewide median (~$54,850), ≥25% of households lacking English proficiency, or a combined minority/income criterion. All 13 municipalities in Suffolk and Middlesex Counties are EJ-designated.

The CIA layer then applies the 33-indicator framework across three categories: pollution burden (PM2.5, diesel, traffic, toxic sites), health outcomes (asthma, cardiovascular disease, life expectancy), and socioeconomic factors (poverty, linguistic isolation, housing burden). The tool flags CIA severity as Very High, High, Moderate, or Low — and generates the compliance documentation framework developers will need for EFSB and local permitting.

- OEJE MassGIS 2020 EJ Population Layer (Census 2020 + ACS 2016–20 five-year)

- Massachusetts CIA Standards & Guidelines (OEJE, issued January 23, 2026; 980 CMR 15.00)

- EPA EJScreen national cumulative impact data (supplementary)

- MA DPH health burden data by census tract (asthma, PM2.5, cardiovascular)

- DOE LEAD Tool for energy burden (% household income spent on energy)

Layer 2: Grid Feasibility & Hosting Capacity

The tool pulls hosting capacity data from Eversource’s Massachusetts Hosting Capacity Map (powered by envelio’s Grid Connection Navigator, launched December 2025), the National Grid Massachusetts System Data Portal (Middlesex County coverage), and the ORNL OpenEnergyHub bulk dataset for Eversource’s Eastern Massachusetts territory. Each municipality receives a hosting capacity rating (Very High, High, Medium, Low) and an interconnection risk level (Very Low, Low, Medium, High, Very High).

Interconnection cost ranges are estimated using Eversource’s published DER Project Costs schedule: overhead point of interconnection ($400K), underground POI above 500 kW ($650K), new transformer upgrade ($4M), conductor reconductoring ($1.0–1.3M/mile), underground cable replacement ($1.9–9.5M/mile). The tool also pulls ISO-NE interconnection queue statistics to flag cluster study participation and median cost benchmarks from LBNL ($148/kW median; $230/kW mean for storage, 2018–21 studies).

|  | DEVELOPER TIP: Substation Proximity Drives Everything Both Chelsea (250 MW Energizar, 0.4 mi to Chelsea substation) and Everett (700 MW Trimount, 0.2 mi to Mystic 345 kV) demonstrate that the highest-scoring BESS sites in Massachusetts sit within half a mile of a major substation on an industrial brownfield. This pattern repeats in every Massachusetts county and should be the first filter in any site search. |
| --- | --- |

Layer 3: Zoning, Permitting & Legal Framework

The tool applies the DOER Model BESS Bylaw three-tier framework to determine the permitting path for each candidate site: Tier 1 (<250 kWh) is by-right in all zones; Tier 2 (250 kWh–10 MWh) is by-right in industrial zones; Tier 3 (10–100 MWh) requires site plan review in industrial zones and special permits in commercial/residential zones. For projects ≥100 MWh, EFSB sole jurisdiction applies effective July 1, 2026 — a consolidated 15-month permit replacing all local, state, and regional approvals, with mandatory auto-approval if the deadline is missed.

Critical legal protections are documented in the tool: the Dover Amendment (M.G.L. c.40A §3) protects standalone BESS from arbitrary municipal prohibition, upheld in Duxbury Energy Storage v. Town of Duxbury ZBA (MA Land Court, June 2025). The Massachusetts Attorney General has rejected every municipal BESS moratorium submitted: Carver (2022), Wendell (2022–2025), Shutesbury (2024), Sherborn (2024), and Blandford (2026). Neither Suffolk County nor Middlesex County contains a single BESS moratorium or ban.

Layer 4: Physical Feasibility & Site Characteristics

The physical feasibility layer estimates maximum BESS capacity (MW) for available parcels using net buildable area after setbacks, power density factors (kW/sq ft for containerized LFP systems), and duration coefficients. Industrial brownfield sites receive scoring bonuses reflecting reduced environmental review burden, established infrastructure access, and eligibility for the federal energy community ITC bonus.

Setback requirements vary by municipality and zoning class — from 50 ft in Chelsea and Everett industrial zones to 100 ft in Winthrop residential zones. Brownfield status is a key accelerant: both top-scoring sites (Everett’s former ExxonMobil terminal and Chelsea’s former commercial site) cleared environmental baseline reviews faster than greenfield alternatives and qualified for additional federal tax credit incentives.

Layer 5: Revenue Modeling & Market Economics

The revenue layer models a complete ISO-NE market stack for each candidate municipality, using the specific load zone (NEMA or SENE) and available market products. This is the layer most commonly under-modeled by developers using Hub averages — the NEMA/SENE zone premium alone adds 1.0–1.5% above Hub prices, and the Forward Capacity Market SENE zone separation (FCA 15: $3.98/kW-month vs. $2.61 rest-of-pool, a 52% premium) is worth an additional $16–$18/kW-year in constrained auction years.

| Revenue Stream | Low ($/kW-yr) | High ($/kW-yr) | Key Driver |
| --- | --- | --- | --- |
| Energy Arbitrage (LMP spread) | $40 | $80 | NEMA DA LMP: $42.09/MWh avg (2024); summer 2025 peak $53.31/MWh |
| Forward Capacity Market (FCM) | $31 | $48 | SENE zone; FCA 18: $3.58/kW-mo; FCA 15 SENE was $3.98/kW-mo |
| Clean Peak Energy Certificates | $15 | $65 | ACP $65/MWh (2026–2032); multipliers up to 25× at monthly system peak |
| Ancillary Services | $2 | $10 | RegD/RegC regulation market; ISO-NE Pay-for-Performance >$9,300/MWh |
| SMART Storage Adder | $10 | $25 | SMART 3.0 (eff. Sep 2025): $0.025–$0.077/kWh; 52 cycles/yr minimum |
| — TOTAL — | $90 | $170+ | 4-hour BESS in NEMA/SENE zone; before ITC |

3.  WHAT RISKS THE TOOL SURFACES BEFORE COMMITMENT

The following risks are routinely discovered late — after site control, interconnection applications, or permitting has begun. The tool surfaces them in pre-acquisition screening.

| Environmental Justice Risk Every municipality in the study area is EJ-designated. The tool identifies CIA severity (Very High in Chelsea, East Boston, Everett) and flags the 33 indicators that must be addressed. Developers who skip CIA pre-screening face permitting holds under 980 CMR 15.00. The tool generates a compliance checklist before you file. Interconnection Cost Risk Underground cable replacement in urban Suffolk/Middlesex ranges from $1.9M to $9.5M per mile. Transformer upgrades cost $4M. A project that models $200K interconnection can face a $2M–$6M actual cost. The tool provides utility-published cost schedules (Eversource DER Project Costs, National Grid FERC tariff) and flags hosting capacity by circuit. Permitting Complexity Risk No BESS-specific zoning exists in most study municipalities. Chelsea required Special Permit + ZBA Variance; the tool identifies this pathway in advance. Revere is actively drafting zoning. The tool flags municipalities where DOER Model Bylaw tiers apply as proxy frameworks and where EFSB jurisdiction (≥100 MWh, July 2026) applies — simplifying large-project permitting to a single 15-month consolidated permit. | Setback & Buildable Area Risk Setbacks range from 50 ft (Chelsea, Everett industrial) to 100 ft (Winthrop residential). A 3-acre site with a 75 ft setback on all sides loses approximately 35–40% of gross area to setback compliance. The tool calculates net buildable area and maximum feasible MW before site acquisition, preventing the common error of acquiring a parcel that cannot physically accommodate the intended system. Revenue Under-Modeling Risk Using the ISO-NE Hub average ($41.47/MWh DA, 2024) instead of the NEMA zone actual ($42.09/MWh) understates LMP revenue by ~1.5% annually. More importantly, the CPS multipliers (up to 25× at monthly system peak) and SMART adders are frequently omitted from pro-formas. The tool models the complete stack, including the near-term resource 2× multiplier for projects with COD before January 1, 2027. Federal Tax Credit Risk Both Chelsea and Everett qualify for the energy community ITC bonus (+10%) due to brownfield / former fossil fuel industrial status. EJ designation in both municipalities supports the low-income community bonus (+10–20%). Failure to document these qualifications before financial close leaves 20–40 percentage points of ITC on the table. The tool identifies qualifying municipalities and bonus tiers by project profile. |
| --- | --- |

4.  HOW THE TOOL SHORTENS TIME-TO-PERMIT

Three concrete mechanisms compress the permitting timeline for developers who use the tool in pre-acquisition screening.

Mechanism 1: EJ-First Design Eliminates Redesign

The most common cause of project delays in Massachusetts BESS development is discovering EJ triggers — CIA requirements, community engagement obligations, health burden documentation — after site control has been established. By embedding CIA screening in the scoring model before any site is shortlisted, the tool eliminates the 6–18 month redesign cycles that follow late EJ discovery. Chelsea’s Energizar project, which proactively engaged GreenRoots and structured a $15M workforce development HCA, moved from Planning Board approval (May 2024) to ZBA permit (October 2024) in five months — a timeline attributable directly to the community engagement framework built in from the start.

Mechanism 2: EFSB Pathway Certainty for ≥100 MWh

Effective July 1, 2026, the EFSB has sole jurisdiction over projects ≥100 MWh, issuing a single consolidated permit replacing all local, state, and regional approvals within a mandatory 15-month deadline. Auto-approval applies if the EFSB misses the deadline. The tool identifies which projects qualify for EFSB jurisdiction versus the local consolidated 12-month path (projects <100 MWh, effective October 1, 2026 for local opt-in). Developers using the tool can target EFSB-eligible sites and plan capital timing around the 15-month runway with regulatory certainty unavailable anywhere else in the country.

Mechanism 3: Data-Ready Host Community Agreements

Host Community Agreement (HCA) negotiations are frequently delayed because developers lack municipality-specific benchmarking data for PILOT values, workforce commitments, and community benefit structures. The tool assembles this data: Chelsea’s 20-year PILOT ($31M total, $1.55M/yr avg) and HCA ($584K/yr workforce development), Everett’s $2.5M/yr tax revenue commitment, and a $45M+ total lifetime community economic impact figure. Developers entering HCA negotiations with these benchmarks — and a CIA compliance framework already documented — move from first meeting to signed agreement months faster than those starting from scratch.

|  | TIMELINE COMPARISON Without tool: Site identified → EJ screening (3–6 months post-identification) → CIA redesign (6–18 months) → Community engagement (6– 12 months) → Permitting (12–18 months) = 27–54 months total. With tool: EJ/CIA pre-screened before site identification → Community engagement structured at acquisition → HCA data benchmarked → EFSB pathway confirmed = 12–20 months total for EFSB-eligible projects. |
| --- | --- |

5.  CHELSEA, MA — DEVELOPER PROFILE: ENERGIZAR PROJECT

Chelsea ranks second overall (113/125) in the five-layer composite scoring and represents the benchmark EJ-forward community benefit model for Massachusetts BESS development. The Energizar project at 284 Eastern Avenue provides a detailed roadmap for developers pursuing similar projects.

| Composite Score Breakdown EJ & Regulatory ■■■■■■■■■■■■■■■■■■■■ 25/25 Grid Feasibility ■■■■■■■■■■■■■■■■■■□□ 23/25 Zoning & Permitting ■■■■■■■■■■■■■■■■□□□□ 20/25 Physical Feasibility ■■■■■■■■■■■■■■■■■□□□ 21/25 Revenue Potential ■■■■■■■■■■■■■■■■■■■□ 24/25 COMPOSITE: 113 / 125 Key Developer Parameters - Site: 284 Eastern Ave, Chelsea (3.7 acres, I-1/I-2 Industrial) - Developer: Flatiron Energy - GC: Consigli Construction - Technology: Containerized LFP units (120+ individual) - Setback: 50 ft (industrial zone) - Permitting: Planning Board (May–Oct 2024) → ZBA (Oct 17, 2024) - Section 83E Round 1: Selected December 19, 2025 - Operations target: End of 2027 - Utility: Eversource (Chelsea electrical substation, 0.4 mi) - ISO-NE zone: SENE (LMP premium: +1.5% above Hub) | Financial Structure (Developer Reference) Item; Value. Est. Capital Investment; $300–$340M. PILOT Agreement; $31M over 20 years ($1.55M/yr avg). Host Community Agreement; $584K/yr — workforce development. Tax increase vs. prior use; 29× (prior: $74K/yr). Total lifetime community benefit; $45M+ (taxes + HCA + workforce). Construction jobs; 100–125 (Consigli Construction). Permanent jobs; Automated; minimal on-site staff. Workforce commitment; $15M+ over 20 years — electrical, HVAC, technical certifications. Federal ITC; Up to 70% (EJ + prevailing wage + energy community). Community Engagement Model - GreenRoots EJ organization as formal project partner from day one - 21-foot screening wall with white roof (urban heat island mitigation) - Tree planting along Eastern Avenue industrial corridor - Wrap-around services for workforce trainees’ families - All permitting hearings conducted with community translation services REPLICATION NOTE Chelsea’s success formula: industrial parcel + adjacent substation + EJ-first community engagement + pre-negotiated HCA before permitting begins + CIA documentation in hand at first Planning Board appearance. The HCA negotiation was completed before the ZBA hearing, removing the primary source of community opposition.. |
| --- | --- |

6.  EVERETT, MA — DEVELOPER PROFILE: TRIMOUNT ESS PROJECT

Everett ranks first overall (119/125) in the five-layer composite scoring. The Trimount Energy Storage project is the largest permitted BESS facility in New England and the dominant case study for large-scale (>100 MWh) EFSB-pathway development in Massachusetts.

| Composite Score Breakdown EJ & Regulatory ■■■■■■■■■■■■■■■■■■■■ 25/25 Grid Feasibility ■■■■■■■■■■■■■■■■■■■■ 25/25 Zoning & Permitting ■■■■■■■■■■■■■■■■■■□□ 22/25 Physical Feasibility ■■■■■■■■■■■■■■■■■■■□ 24/25 Revenue Potential ■■■■■■■■■■■■■■■■■■□□ 23/25 COMPOSITE: 119 / 125 Key Developer Parameters - Site: 52 Beacham Street, Everett (20.75 acres, I-2 Heavy Industrial) - Developer: Jupiter Power (BlackRock platform) - Technology: Hithium LFP containerized units - Setback: 50 ft (I-2 industrial zone) - Permitting: EFSB Docket 25-05 → Final approval February 27, 2026 - Section 83E Round 1: Selected December 19, 2025 - Grid connection: Two underground lines (115 kV + 345 kV) to Mystic Substation - Utility: Eversource (Mystic 345 kV substation, 0.2 mi) - ISO-NE zone: SENE (highest hosting capacity in study area) | Financial Structure (Developer Reference) Item; Value. Total Capital Investment; >$1 billion. Land acquisition; $72.5M (The Davis Companies, from ExxonMobil). Environmental cleanup; ~$100M (largest MA Brownfields Covenant Not to Sue in history). Tax revenue; $2.5M/yr avg over 20 years (vs. prior $200–$300K/yr — 20× increase). Total 20-year tax contribution; $50M+ (Jupiter Power estimate). Transmission deferral; $2.2B (Jupiter Power bid estimate; not independently verified). Construction jobs; Hundreds (Project Labor Agreement; union labor). Apprenticeship; Everett High School pipeline; local hiring preference. Federal ITC; Up to 70% (brownfield + EJ + prevailing wage + domestic content). Capacity market (FCA 18); $42.96/kW-yr = ~$30M/yr for 700 MW facility. EFSB PATHWAY LESSON Trimount’s EFSB route (Docket 25-05) provided complete permitting certainty and preempted the Everett mayor’s opposition. Once the EFSB accepted jurisdiction, no municipal approval was required. Effective July 1, 2026, all projects ≥100 MWh automatically qualify for this pathway. For large BESS, EFSB is faster, more certain, and immune to local political risk.. |
| --- | --- |

7.  REVENUE OPTIMIZATION & INCENTIVE STACKING

Massachusetts offers one of the strongest BESS revenue environments in the United States due to the convergence of ISO-NE NEMA/SENE zone pricing, the Clean Peak Energy Standard multiplier structure, SMART storage adders, and a federal ITC stack that can reach 70% for projects in EJ brownfield locations.

ISO-NE Pricing Advantage — NEMA/SENE Zone

The NEMA load zone (most of Suffolk County and Cambridge) and SENE capacity zone (all Suffolk County, most Middlesex County) are the highest-priced nodes in the ISO-NE grid. In 2024, the NEMA Day-Ahead LMP averaged $42.09/MWh versus the Hub average of $41.47/MWh — a consistent 1.0–1.5% premium. During the June 24, 2025 scarcity event (extreme heat, 2,550 MW unexpected unavailability), wholesale prices reached approximately $1,600/MWh in the afternoon peak, with the ISO-NE’s Pay-for-Performance mechanism triggering at >$9,300/MWh. The Cranberry Point BESS (150 MW, Carver MA) earned approximately $1,110/MWh during this event — the first large-scale demonstration of storage’s capacity market revenue under real scarcity conditions.

Clean Peak Energy Standard (CPS) Multiplier Stack

The CPS Alternative Compliance Payment rises to $65/MWh for 2026–2032 under October 2024 emergency rulemaking. CPECs trade at 2–8% below ACP. Four multipliers can be stacked:

- Seasonal multiplier: up to 4× (summer, May–October)

- Monthly system peak multiplier: up to 25× (actual monthly system peak hour)

- Distribution Circuit Multiplier: 2× for 10 years on pre-identified circuits

- Near-Term Resource Multiplier: 2× for 10 years on up to 50 MW front-of-meter storage, COD before January 1, 2027

Federal ITC Stacking Guide (OBBBA, July 2025)

| ITC Component | Rate | How to Qualify | Applies to Both Sites? |
| --- | --- | --- | --- |
| Base ITC (Section 48E) | 6% | Default — all BESS projects | Yes |
| Prevailing Wage & Apprenticeship | 30% (total) | Certified compliance for projects >1 MW; mandatory | Yes |
| Domestic Content Bonus | +10% (40% total) | US-produced steel, iron, manufactured products | Challenging — most LFP cells manufactured in China; FEOC rules apply 2026 |
| Energy Community Bonus | +10% (50% total) | Brownfield, closed coal plant, or high-unemployment fossil fuel community | Chelsea: Yes (industrial site). Everett: Yes (former oil terminal). |
| Low-Income Community Bonus | +10–20% (up to 70% total) | Low-income census tract or serving low-income residents | Both: Strong case given 100% EJ block group designation |
| Maximum Stackable ITC | Up to 70% | PWA + Energy Community + Low-Income bonuses | Both sites qualify |

Duration Optimization by Site

Battery duration selection drives which revenue streams are most accessible. The tool recommends duration based on site location, hosting capacity, and grid node characteristics:

- Everett (Mystic Substation, Very High hosting capacity): 8-hour system recommended — maximizes FCM capacity payments, qualifies for long-duration 83E contracts, and captures overnight arbitrage

- Chelsea (Eversource Chelsea Substation, High capacity): 4-hour system recommended — optimal for CPS peak multipliers, FCM participation, and SMART adder eligibility

- East Boston, Revere, Cambridge (Medium capacity): 2-hour systems recommended — behind-the-meter peak shaving, ConnectedSolutions ($275/kW summer), demand charge reduction

8.  PRACTICAL NEXT STEPS FOR DEVELOPERS

The following action sequence is drawn directly from the Chelsea and Everett project timelines and represents the fastest path to permit in Suffolk or Middlesex County.

Pre-Acquisition (Before Any Site Commitment)

- Run the five-layer MCE score on candidate municipalities and specific parcels

- Confirm EJ designation status and CIA severity for target census block groups

- Pull Eversource or National Grid hosting capacity data for candidate circuits (envelio Navigator or ORNL OpenEnergyHub)

- Estimate Max MW using net buildable area after applicable setbacks (50–100 ft)

- Model full revenue stack using NEMA or SENE zone LMP, not Hub average

- Identify ITC bonus eligibility: brownfield? EJ census tract? Prevailing wage?

Site Control Through Permitting

- Retain EJ/CIA consultant before submitting any permit applications

- Engage with the municipal Environmental Justice community organization from day one

- Pre-negotiate Host Community Agreement framework before first public hearing

- Determine EFSB vs. local permitting path based on project MWh capacity

- For ≥100 MWh: file EFSB petition; lock in 15-month permitting runway (effective July 2026)

- Prepare CIA documentation addressing all 33 indicators; submit with application package

Interconnection & Commercial

- File ISO-NE interconnection application after EFSB approval (or in parallel for local-path projects)

- Develop Section 83E procurement bid in parallel with permitting — Round 2 target ~1 GW (2026)

- Negotiate 20-year CPEC contract structure; retain wholesale energy and FCM upside

- Certify prevailing wage and apprenticeship requirements before financial close to secure 30% base ITC

- Document energy community and low-income community bonus eligibility before financial close

9.  DATA SOURCES & CITATIONS

| Source | Organization | URL / Reference |
| --- | --- | --- |
| MassGIS 2020 EJ Population Layer | MassGIS / OEJE | mass.gov/massgis · Census 2020 + ACS 2016–20 5-yr |
| CIA Standards & Guidelines | OEJE | 980 CMR 15.00 (issued Jan 23, 2026) |
| Eversource Hosting Capacity Map | Eversource / envelio | eversource.com/interconnections/ma/hosting-capacity-map |
| Eversource DER Project Costs | Eversource | Published July 2021–2022 |
| National Grid MA System Data Portal | National Grid | systemdataportal.nationalgrid.com/MA/ |
| U.S. DOE Hosting Capacity Atlas | DOE / CMEI | energy.gov/cmei/us-atlas (updated Jul 2025) |
| ISO-NE 2024 Annual Markets Report | ISO-NE | iso-ne.com (May 2025) |
| ISO-NE FCA Results (FCA 14–18) | ISO Newswire | isonewswire.com |
| ISO-NE 2024 EMM Report | ISO-NE | iso-ne.com/static-assets/documents/100025/ |
| NREL 2025 Battery Cost Projections | NREL | DOI: 10.2172/2583471 |
| NREL 2024 Annual Technology Baseline | NREL | atb.nrel.gov/electricity/2024/ |
| DOER Model BESS Bylaw | MassDOER | mass.gov (Oct 6, 2025) |
| MA 2024 Climate Act Chapter 239 | MA Legislature | Signed November 20, 2024 |
| Pierce Atwood Chapter 239 Analysis | Pierce Atwood LLP | pierceatwood.com (Nov 2024) |
| Energizar project details | Flatiron Energy | energizar.energy |
| Trimount ESS project details | Jupiter Power | trimountenergy.com |
| Chelsea Record (PILOT & permitting) | Chelsea Record | chelsearecord.com (Jul & Oct 2024) |
| Boston Globe (Everett coverage) | Boston Globe | bostonglobe.com (May & Dec 2024, Dec 2025) |
| CommonWealth Beacon (83E Round 1) | CommonWealth Beacon | commonwealthbeacon.org (Dec 2025) |
| pv magazine USA (83E Round 1) | pv magazine USA | pv-magazine-usa.com (Dec 2025) |
| MassCEC 2024 Annual Report | MassCEC | reports.masscec.com/2024/ |
| MA Zoning Atlas | National Zoning Atlas / Suffolk Univ. | zoningatlas.org/massachusetts |
| LBNL Interconnection Cost Analysis | Lawrence Berkeley National Lab | Jun 2023 |

This document is prepared for informational purposes only. It does not constitute legal, regulatory, or financial advice. Developers should engage qualified legal counsel for EJ compliance, interconnection applications, and incentive tax credit structuring. All data current as of April 2026.